## Fiscal-Financially Sound
2011-2013 Strategic Plan Progress Summary March 1, 2013
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Last Update | Status | Notes
Fiscal/Financially Sound | Iowa One Call will manage all financial resources efficiently to support all operational and capital needs by strategically executing financial forecasting and by establishing revenue/expenditures stability.
Action Plan # 1: Set and maintain reserve levels at a defined percentage of annual income based on history and financial forecasting. | Steve, Craig | 2011-04-30 | 2011-06-24 | 2013-03-01 | Complete | Continuation of reserve levels & revenues.
» 1a. Board to set reserve levels by April 30, 2011. | Board | 2011-04-30 | 2011-06-24 | 2013-03-01 | Complete
» 1b. Complete annual assessment of reserves during annual budget process and adjust accordingly. | Board | 2011-04-30 | 2011-06-24 | 2013-03-01 | Complete
Action Plan # 2: Assess current and future building needs, current lease options and other building alternatives with board recommendations by January 1, 2012. | Steve, Craig | 2012-01-01 | 2011-09-08 | 2013-03-01 | Complete | Needs of building & costs were reviewed with the current location accepted.
Action Plan # 3: Evaluate alternative revenue sources and make board recommendations for utilization by September 2012. | Steve, Craig | 2012-09-01 |  | 2013-03-01 | Complete | Ongoing efforts are underway to define new opportunities, and to develop and implement additional internal and external changes designed to enhance revenue sources.

## Leadership-Governance
2011-2013 Strategic Plan Progress Summary March 1, 2013
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Last Update | Status | Notes
Leadership/Governance | Iowa One Call is committed to providing the highest level of leadership to assure long-range professional development and quality programming. Iowa One Call's future workforce needs will be met through effective succession planning and skill development initiatives.
Action Plan # 1: Analyze current board qualifications, term lengths, required participation and contributions and make board recommendations as needed by January 1, 2013. | Execuitve Committee | 2013-01-01 |  | 2013-03-01 | complete | Ex. Commity has effectively addressed this action item.
Action Plan # 2: Establish a tactical plan for dealing with the succession of board member retirements, with board recommendations by January 1, 2013. | Executive Committee, Craig | 2013-01-01 |  | 2013-03-01 | complete | Ex. Commity has effectively addressed this action item.
Action Plan # 3: Establish a tactical plan for dealing with the succession of the Administrative Director, with recommendations to the Executive Committee by December 31, 2011. | Executive Committee, Craig | 2011-12-31 | 2012-12-08 | 2013-03-01 | Complete | A plan was developed/approved by the Board and has been incorporated into a contract approved by the Board and accepted by Walter & Associates
Action Plan # 4: Analyze current and future administrative and staff needs and make recommendations to the board for modifications by December 31, 2011. | Executive Committee, Craig | 2011-12-31 | 2012-12-08 | 2013-03-01 | Complete | Changes to Admin Office started July 1, 2012
Action Plan # 5: Develop a bi-annual review process for evaluating the call center vendor by August 2, 2011. | SOTA, Craig | 2011-08-01 | 2011-08-23 | 2013-03-01 | Complete | Process is in place.
Action Plan # 6: Assess call center security and develop a plan to identify needs by July 2011. | Craig | 2011-07-01 | 2011-10-31 | 2013-03-01 | Complete | Security system is in place

## Legislative
2011-2013 Strategic Plan Progress Summary March 1, 2013
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Last Update | Status | Notes
Legislative | Iowa One Call will provide effective input to the processes that impact policy-making, laws and regulations related to protecting underground facilities.
Action Plan # 1: Develop a plan for sponsoring legislation to include all pertinent steps in the process to change the Iowa Code, Chapter 480 by November 1, 2011. | Leon,Craig, Ben | 2011-11-01 | 2012-01-09 | 2013-03-01 | Completed | Ongoing updates as needed
Action Plan # 2: Develop legislation for changing Iowa Code, Chapter 480 by the 2013 legislative session. | Leon,Craig, Ben | 2013-01-01 |  | 2012-03-01 | In Progress | Socialization with IUB has been completed. Committee will move forward with developing proposed language…

## Outreach-Communication
2011-2013 Strategic Plan Progress Summary March 1, 2013
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Last Update | Status | Notes
Outreach/Communications | Iowa One Call is committed to executing effective outreach, marketing and education programming that pertains to underground damage prevention and excavation safety and speaks to the values, interests and well-being of all members, stakeholders and Iowa communities.
Action Plan # 1: Assess current marketing programs to determine effectiveness and make board recommendations for the next three years of programming by August 1, 2011. | Advertising Committee, Ben | 2011-08-01 | 2011-07-01 | 2013-03-01 | Complete | The 2011-2012 Advertising Committee implemented an advertising RFP to ten (10) Iowa agencies and met March 15, 2012 to oversee a pre-bid meeting. The official proposals were received in April. The RFP was designed to garner new and fresh perspectives and potential options/opportunities via proposals that were assessed for efficiency and effectiveness.
Action Plan # 2: Develop and implement an external communications program designed to garner collaborative damage prevention partnerships to coincide with three-year marketing program by March 2012. | Advertising Committee, Ben | 2012-03-01 | 2011-2012 phase completed | 2013-03-01 | Complete | 2011 programming effectively and successfullyl completed. 2012 programming effectively and successfully completed. Board approved Committee to award a new ntract to the Cedar Rapids-based agency, HRB. The committee has approved a campaign for 2013, which the agency is currently developing and which is on track for implementation in April, 2013.
Action Plan # 3: Develop and implement custom training to address key system abusers to coincide with three-year marketing program. | Advertising Committee, SOTA Committee,Ben | 2011-03-01 |  | 2013-03-01 | Complete | Targeted programming, featuring custom presentations, have been successfully implemented at multiple Iowa contractor/excavator companies, engineering firms and facility operator organizations throughout 2011, 2012 and into 2013. Joint partnerships with multiple IOC member operator organizations has resulted in multiple custom presentations/programs targeting system abusers. Continued efforts and programming will be developed and implemented throughout 2013.
Action Plan # 4: Develop procedures for updating and maintaining the Iowa One Call website with initial updates completed by July 31, 2011. | Advertising Committee, Ben | 2011-07-31 | 2011-08-15 | 2013-03-01 | Complete | Ongoing updates are handled in-house, with exception to major changes that require altering embedded software, in which cases outsourcing is implemented with one of the two vendors, AIA, or WebSpec Design.
Action Plan # 5: Develop, produce and distribute a new comprehensive Board Member Handbook to all board members by December 31, 2011. | Staff, Craig | 2011-12-31 | 2011-12-30 | 2013-03-01 | Complete | The comprehensive Board Member handbook has been designed electronically as the Board Member Files posted at and accesible only via the Secure Board Page located in conjunction with the IOC website.
Action Plan # 6: Design and implement a web-based secure communications system for Iowa One Call Board of Directors by September 1, 2012. | Advertising Committee, Ben | 2012-09-01 | 2012-02-01 | 2013-03-01 | Complete | The secure Board Members page is routinely updated inhouse and accessible to all Iowa One Call Board Members via a secure login process, which each Board Member must setup a personal login.

## Technology
2011-2013 Strategic Plan Progress Summary March 1, 2013
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Last Update | Status | Notes
Technology | Iowa One Call is committed to maintaining the latest, most cost-efficient technologies and technological improvements in order to provide all stakeholders with the most accurate data available in the most effective manner.
Action Plan # 1: Develop board recommendations for enhancing the Design Request System by November 1, 2011. | SOTA Committee | 2011-11-01 |  | 2013-03-01 | Completed | The Committee has met and made a presentation at the Mid-Iowa Association of Land Surveyors on Nov. 30. Enhancements to the ITIC will have some impact on the DRS. OCC is working on identified enhancements.
Action Plan # 2: Implement enhancements to the ticket management system to improve the overall effectiveness of the underground facilities locating system and processes by March 31, 2012. Areas to be addressed include: white-lining, life of a ticket, re-locates, joint meets, ticket abuse, and identifying dig-site location. | SOTA Committee | 2012-03-31 |  | 2013-03-01 | In progress | A script was developed to be used by CSRs asking the caller to verify that the ticket is a compliant ticket. Four Committee members attended the OCC User's Conference in St. Louis. Our DRS is so different from other OCC states that no comparison was viable. Ongoing staff-conducted training for system abusers has been implemented and will continue... A new set of "abusers" has been developed and we are working with them to correct the problem. The Committee will continiue to work with OCC towards addressing this area of abuse.
Action Plan # 3: Develop and implement a plan with a goal of 100% electronic ticketing (excluding Emergency Notifications), with 50% electronic ticketing realized by November 1, 2013. | SOTA Committee | 2013-11-01 |  | 2013-03-01 | In progress | Call Center is socializing (educating callers) about online ticketing during each call received, which has resulted in growing the number of ITIC users.Callers who are receptive, are directed to the training website. The development of ITIC "Lite" (ITIC for Homeowners) has been completed and is scheduled to launch March 4, 2013. Current ITIC usage is more than 45-percent.