## Fiscal-Financially Sound
2013-2015 Strategic Plan Progress Summary Sept. 4, 2014
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Status | Notes
Fiscal/Financially Sound | Iowa One Call will manage all financial resources efficiently to support all operational and capital needs by strategically executing financial forecasting and by establishing revenue/expenditures stability.
Action Plan # 1 Incorporate reserve levels into the budget process annually. | Finance Committee | Dec / Annually |  | 2014 completed | Reserve levels have been reviewed by the Executive Committee and effectively established for 2014.
Action Plan # 2 Develop and implement a financial model to provide funds to be used for reaching the Vision Statement by January 1, 2015 | Finance Committee | 2015-01-01 |  | In Progress | Part of the review process for both the Financial and Executive Committees. One of the primary objectives of the Financial Committee and the Secretary/Treasurer. The aforementioned groups will continue to work on this action.
Action Plan # 3 Evaluate our disaster recovery contingency and the vendor staffing status annually to ensure business continuity. To be completed within the first quarter annually. | Finance Committee, Craig / Staff | March / Annually |  | Ongoing | Administrative Director is in routine contact/follow up with OCC regarding both areas and continually reviews the process. The IOC Board and Admin Dir. Have approved of the current disaster recovery process and continue to review this action item.

## Leadership-Governance
2013-2015 Strategic Plan Progress Summary Sept. 4, 2014.
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Status | Notes
Leadership/Governance | Iowa One Call is committed to providing the highest level of leadership to assure long-range professional development and quality programming.
Action Plan # 1 Develop and implement a performance review process for excavators to evaluate Iowa One Call by June 1, 2013 | Executive Committee Craig / Staff | 2013-06-01 |  | complete | A custom survey page has been developed and implemented on the IOC website. Staff has implemented a statewide outreach program to notify excavators - asking them to take the survey. Tracking is in place.
Action Plan # 2 Evaluate the need to establish excavator and/or designer advisory teams by November 1, 2013 | Executive Committee Craig / Staff | 2013-11-01 |  | Complete | Planning meetings have been held with the IOC Class B Board Director, John Barber and admin. John Barber has discussed this matter with representatives of NUCA, AGC, and the Iowa Engineers Society. Upon evaluation, the preliminary position is that one advisory team comprised of both designers and excavators will provide the IOC Board with valuable insight into the needs of these two important stakeholder groups. John will also bring this matter to the attention of CGI. Implementation is the next phase and will be addressed by the Executive Committee

## Legislative
2013-2015 Strategic Plan Progress Summary Sept. 4, 2014
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Status | Notes
Legislative | Iowa One Call will provide leadership and input to the processes that impact policy-making, laws and regulations related to protecting underground facilities.
Action Plan # 1 Assess the adequacy of current Iowa Code Chapter 480 enforcement and dispute resolution processes by September 1, 2014. | Legislative Committee | 2014-09-01 |  | Ongoing | 2014: IOC and IUB have completed the State Assessment for Damage Prevention as administered by PHMSA. Legislative Committee has been in discussions and will continue assessments regarding this matter. Staff has been in discussions with IUB and PHMSA regarding Iowa enforcement protocols and the matter of dispute resolution. Dispute resolution was not included as a candidate item for amendment changes during the 2014 Iowa Legislative Session, but may be considered for future proposals.
Action Plan # 2 Provide recommended revisions to the Iowa Code Chapter 480 for Board review annually. | Legislative Committee | Fourth Quarter |  | Completed | After approving the Legislative Committee's Proposed Legislative Amendments, the Board directed Craig Walter to present the Iowa legislature with the proposed amendments for bill drafting - resulting in HSB518, which has passed the Commerce Committee and is currently being considered by the House (HF2408); The HF may be brought to the floor for discussion on March 6, 2014; Governor Terry Branstad signed the bill into law on March 26. The new laws will become effective on July 1, 2014.
Action Plan # 3 Provide underground facilities damage prevention language that can be recommended for incorporating into construction documents by June 1, 2014. | Legislative Committee | 2014-06-01 |  | In Progress | A new logo has been developed and is being distributed to the professional design community. Further planning efforts have been discussed with the Class B IOC Director representing excavators. New planning will resume with the new Class B Director and CGI officers and members. Admin will continue to work with John Barber (representing the design community)

## Outreach-Communication
2013-2015 Strategic Plan Progress Summary Sept. 4, 2014
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Status | Notes
Outreach/Communications | Iowa One Call is committed to executing effective outreach, marketing and education programming that protects underground facilities and speaks to the values, interests and wellbeing of all members, stakeholders and Iowans.
Action Plan # 1 Analyze 2012 dig-in data to determine common causes of underground facilities damage by October 1, 2013. | Ad Committee | 2013-10-01 | In progress | Current trends (information shared by MidAmerican Energy, USIC-Locating, Iowa Utilities Board, and the IA AG's Office) show common causes: 1) Multiple pipeline incidents resulted in Iowa during 2012-2013 due to tilers not making required notification to IOC; and 2) Inappropriate /insufficient digging techniques at the dig site. IOC has developed and is implementing targeted programming aimed at known violators (ESAP Ag/Pipeline programs, and custom contractor presentations/meetings). The Information obtained correlates with the national DIRT Report. Admin staff continue to use IOC "Dig-In" tracking to target excavators with instances of, or multiple instances of Dig-Ins with communications (in person visits, phone contacts and written communications). Board recommendation: Work on obtaining permission to have access to the dig-in reporting/data from member operators since that data is known to be more conclusive than the call center tracking for determing cause. Staff will continue working with the appropriate committees to formulate strategies for accessing operator data.
Action Plan # 2 Develop plans applying best practices that fit the needs of Iowa One Call to correct excavator and facility operators / owners by November 1, 2013. | Ad Committee | Nov. 1, 2013 | complete | The 2014 Excavation Safety Awareness Program (ESAP) and the 2014 Pipeline and Agricultural Excavation Safety Program (PAESP) will feature several segments on applying the recommended best practices. Current social media and advertising campaign elements include the recommended usage of best practices during excavation. Additionally, the new legislative amendments conform with the Best Practices; the CGA Best Practices were a primary reference/model for determining legislative candidate items and for developing the new laws.
Action Plan # 3 Assess current marketing programs to determine effectiveness and make Board recommendations by August 1, 2014 | Ad Committee | 2014-08-01 | Ongoing | The Advertising Committee has established and presented Board recomendations for 2014 programming; resulting in an approved 2014 programming budget, with assigned programming to be implemented by the agency Amperage (formerly HRB), and via In-House efforts. A portion of the 2014 approved advertising budget remains in reserve for use in developing potential program/event opportunities. The 2014 campaign will focus on enhancing the social media campaign begun in 2013, and by developing traditional media Public Service Announcements.
Action Plan # 4 Evaluate the Iowa One Call website and social media programs annually at the end of third-quarter. | Ad Committee | Sept / Annually | complete | Upon analysis of the web site, the Advertising Committee, the Executive Committee and the Administrative staff have concluded that the general lack of cyber security provided by the current web host is insufficient for IOC needs. Consequently, IOC will work with One Call Concepts on web hosting, maintenance and design duties in 2014. Initial planning is underway for transitioning the current site over to OCC.
Action Plan # 5 Implement the use of user-training resources to excavators, designers, homeowners and facility operators. To be an ongoing program reviewed annually during fourth-quarter. | Ad Committee | Nov. / Annually | Ongoing | 2014 training / programming efforts include the distribution and presentation of new user training materials/programs, including two new training videos - produced for the 2014 ESAP programs, as well as existing collateral promotional materials and programming. Staff has successfully completed a number of custom training/education program/presentation in the first half 2014 (through August), including key speaking engagements at the LICA Conference, SEDC Conference at ISU, IOWWA Conference, PCI Conference, Iowa REC Conference, AWWA Conference, Iowa Communications Alliance, MEC Training Courses, CGI Membership Meetings, and other smaller damage prevention meetings (e.g.: Waukee Public Works, IAMU training, etc.). IOC has also participated in two major Home & Garden Shows, an 811-Day Consumer Event, and the Iowa State Fair - where custom literature and educational materials were distributed, and where the various audiences were addressed by staff.
Actin Plan # 6 Develop a communications plan targeting local / state public officials by November 1, 2013 | Ad Committee | Nov. 1, 2013 | complete | Currently, key contact agencies at the local and state level have been added to the IOC Newsletter email list. Prior to the next newsletter release, these new contacts will be sent an email introducing them to Iowa One Call and inviting them to continue receiving the newsletter and encouraging them to pass the newsletter along to their constituents. Follow up contact will be made via the telephone and email system, with posible in-person meetings if applicable. Staff will continue to work with various committees to develop new programming options...

## Technology
2013-2015 Strategic Plan Progress Summary Sept. 4, 2014
Key Results Areas Checklist
Key Results Area | Assigned To | Target Date | Completed Date | Status | Notes
Technology | Iowa One Call is committed to maintaining the latest, most cost-efficient technological improvements.
Action Plan # 1 Develop Board recommendations for enhancing/improving communications through the use of social media and information technologies by December 31, 2013 | SOTA | Dec. 31, 2013 |  | completed | The Advertising Committee has selected Social Media as the primary element of the 2013 and 2014 advertising campaign. The agency, HRB, will continue implementing a full scale social media Ad Words Campaign throughout 2014. The Advertising Committee identified areas within the 2013 social media campaign that needed improvments and has directed staff to work with HRB to enhance the Ad Words program. Additionally, administrative staff is currently implementing ongoing updates to key IOC social media programs and will begin working with OCC in January to implement enhancements to the IOC website.
Action Plan # 2 Develop Board recommendations for implementation of a statewide electronic positive response system to be utilized on 98-percent of outbound ticket volume by August 1, 2013. | SOTA | Aug. 1, 2013 |  | completed | The Board has approved the SOTA Committee's recommendations for implementing an Electronic Positive Response System; and has also approved the proposed legislative amendments to Iowa Code, Chapter 480, used to develop HSB518, which has been moved to House File (HF2408).
Action Plan # 3 Develop and implement a plan with a goal of 100-percent electronic ticketing; with 75-percent electronic ticketing realized by November 1, 2016. | SOTA | Nov. 1, 2016 |  | In progress | OCC is promoting ITIC usage at the point of contact at the call center. Staff has posted promotional information about ITIC and ITIC "Lite" on the IOC website. The agency HRB has been directed to increase the usage of ITIC 'Lite" via educational/communications programming, and will implement enhanced social media advertising in 2014 targeting homeowners with messages that promote Itic usgae. An overview of ITIC was included in the 2014 ESAP slide presentation. A new trade show display was purchased featuring a prominent ITIC display.
Action Plan # 4 Evaluate our electronic infrastructure against potential threats from cyber attacks by November 1, 2013. | SOTA | Nov. 1, 2013 |  | completed | The administartion has posted the Cyber Security Process, as implemented by One Call Concepts, to the IOC Board Member Page
Action Plan # 5 Develop and implement a plan for uploading dig-site information into the ticket management system by December 31, 2014. | SOTA | Dec. 31, 2014 |  | In progress | Preliminary discussion has taken place with One Call Concepts, and is slated for SOTA Committee review and planning.